## Implementation Timeline
QMetry AUDIT LOG SYSTEM - COMPREHENSIVE IMPLEMENTATION TIMELINE
Month 1 | → | PHASE 1: Phase 1: Requirements & Analysis
DURATION: 3 Weeks TEAM: Business Analysts, QA Architects, Stakeholders KEY DELIVERABLES: • Comprehensive requirements specification document • Stakeholder analysis and communication plan • Regulatory compliance assessment (SOX, GDPR, HIPAA) • User story mapping with acceptance criteria • Non-functional requirements definition • Risk assessment and mitigation strategies DETAILED ACTIVITIES: • Interview all key stakeholders across departments • Analyze existing audit processes and pain points • Document current system integrations and dependencies • Define data retention and archival policies • Establish performance benchmarks and SLAs • Create detailed use case scenarios • Validate requirements with legal and compliance teams • Prioritize features using MoSCoW methodology
Month 2 | → | PHASE 2: Phase 2: System Architecture & Design
DURATION: 4 Weeks TEAM: System Architects, Database Designers, Security Engineers KEY DELIVERABLES: • High-level system architecture diagrams • Database schema design with optimization strategies • Security architecture and threat model • Integration architecture for existing systems • Scalability and performance design • Disaster recovery and backup strategy DETAILED ACTIVITIES: • Design microservices architecture with service boundaries • Create database partitioning and sharding strategy • Design event sourcing and CQRS patterns • Plan API gateway and service mesh architecture • Design caching strategies (Redis, CDN) • Create monitoring and observability architecture • Design CI/CD pipeline and deployment strategies • Security review and penetration testing planning • Create proof-of-concept for critical components
Month 3 | → | PHASE 3: Phase 3: Core Development Sprint 1
DURATION: 6 Weeks TEAM: Backend Developers, Database Engineers, DevOps KEY DELIVERABLES: • Core audit event capture system • Database infrastructure with basic tables • Authentication and authorization system • Basic API endpoints for event logging • Unit test coverage > 80% • CI/CD pipeline implementation DETAILED ACTIVITIES: • Implement event interceptors for all 10 event types • Develop actor identification and context capture • Build immutable audit data storage with encryption • Implement basic filtering and query capabilities • Create REST API with OpenAPI documentation • Set up monitoring and logging infrastructure • Implement automated testing frameworks • Database migration scripts and version control • Security scanning and vulnerability assessment • Performance baseline establishment
Month 4 | → | PHASE 4: Phase 4: Advanced Filtering & Reporting
DURATION: 5 Weeks TEAM: Full-stack Developers, UI/UX Designers, QA Engineers KEY DELIVERABLES: • Advanced multi-dimensional filtering system • PDF report generation with professional formatting • Web-based user interface for audit log viewing • Email scheduling and notification system • Integration test suite completion • Performance optimization implementation DETAILED ACTIVITIES: • Develop hierarchical project and module filtering • Implement flexible date range selection with presets • Create user and team-based filtering with RBAC • Build PDF generation with charts and visualizations • Design responsive web UI with modern frameworks • Implement email template system with customization • Create scheduled job management interface • Optimize database queries with proper indexing • Load testing and performance tuning • Accessibility compliance (WCAG 2.1 AA)
Month 5 | → | PHASE 5: Phase 5: Enterprise Features & Scalability
DURATION: 4 Weeks TEAM: Senior Developers, Performance Engineers, Security Team KEY DELIVERABLES: • Horizontal scaling capabilities • Advanced security features (encryption, audit trails) • Enterprise integrations (LDAP, SAML, OAuth) • Advanced analytics and dashboard • Mobile-responsive interface • Admin management console DETAILED ACTIVITIES: • Implement database sharding and read replicas • Add support for multiple authentication providers • Create role-based access control with fine-grained permissions • Build real-time dashboards with websockets • Implement data export in multiple formats (CSV, JSON, XML) • Add support for custom report templates • Create audit log for the audit system (meta-auditing) • Implement rate limiting and DDoS protection • Add support for webhook integrations • Mobile app development or PWA implementation
Month 6 | → | PHASE 6: Phase 6: Testing & Quality Assurance
DURATION: 4 Weeks TEAM: QA Engineers, Performance Testers, Security Testers KEY DELIVERABLES: • Comprehensive test execution results • Performance test report with benchmarks • Security assessment and penetration test results • User acceptance testing completion • Bug fixes and system stabilization • Documentation completion DETAILED ACTIVITIES: • Execute comprehensive functional test suite • Perform integration testing across all system components • Conduct performance testing under various load conditions • Execute security testing including penetration tests • Perform usability testing with real users • Conduct accessibility testing and remediation • Execute disaster recovery and backup testing • Validate data migration and import/export processes • Cross-browser and cross-platform compatibility testing • Automated regression test suite implementation
Month 7 | → | PHASE 7: Phase 7: Deployment & Go-Live
DURATION: 3 Weeks TEAM: DevOps Engineers, System Administrators, Support Team KEY DELIVERABLES: • Production environment setup and configuration • Data migration from legacy systems completed • User training materials and sessions completed • Monitoring and alerting systems operational • Support processes and documentation ready • Go-live and post-deployment support DETAILED ACTIVITIES: • Set up production infrastructure with high availability • Execute data migration with validation and rollback plans • Configure monitoring, logging, and alerting systems • Conduct user training sessions for different user groups • Create operation runbooks and troubleshooting guides • Implement backup and disaster recovery procedures • Execute go-live checklist and readiness review • Monitor system performance and user adoption • Provide immediate post-launch support and bug fixes • Collect user feedback for future enhancements
Month 8 | → | PHASE 8: Phase 8: Post-Launch Support & Enhancement
DURATION: Ongoing TEAM: Support Engineers, Product Managers, Development Team KEY DELIVERABLES: • System stability and performance monitoring • User feedback collection and analysis • Enhancement roadmap and priority planning • Continuous improvement implementation • Knowledge transfer and documentation updates • Success metrics and ROI analysis DETAILED ACTIVITIES: • Monitor system performance and user adoption metrics • Provide technical support and issue resolution • Collect and analyze user feedback for improvements • Plan and implement incremental feature enhancements • Regular security updates and vulnerability patches • Capacity planning and infrastructure scaling • User community building and best practice sharing • Regular system health checks and optimization • Compliance audits and regulatory reporting • Long-term maintenance and evolution planning